## Sheet1
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
User Story ID | <Provide unique ID for each User story>
User Story Name | <Provide the theme/name of the User story or a high level requirement>
Eg: User login
Registration
Mail notification
User Story Role | < Provide who would be end User of the User story>.
Details of who would use that functionality
Eg:End User
Admin
Teacher
Conference attendee
User Story Details | <Provide description of what the User want>
Provide details on "As a/an" particular user what the user wants.
Eg: As a conference attendee, I want to be able to register online
Acceptance criteria | <Specify the Acceptance criteria>
Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended.
So for the above example, the acceptance criteria could include:
A user cannot submit a form without completing all the mandatory fields
Information from the form is stored in the registrations database.
Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story.
Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
Done | Yes/No field, that can be selected from drop down based on an user is completed or not
Added in Sprint | Provide sprint number when the particular User Story was handled
Closed in sprint | Provide sprint number when the particular User Story was completed
Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)

## Sheet2
Product Backlog <ONLINE BAKERY>
Project ID: INTADM22JF056 C3: Protected POD-1
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
1 | Registration Function | End user | Allows a new user to create an account which stores the details in the database, in order to shop the products and proceed with payment.On successful registration,the user receives an email. | All fields need to be entered correctly. | 5
2 | Login Function and Forgot Password | End user | Can login to the web application with their credentials. In case the user forgets their password, they can reset the same. | The username and password should be filled correctly. | 5
3 | Best Selling items | End user | Can allow users to check best selling items and order them. | Need to enter the correct login details. | 5
4 | Shop | End user | Allows users to select products by searching through category or by product name. User can also check the FAQs. | Users need to click the add to cart button. | 5
5 | Add to Cart | End user | Allows user to add the items they want to order to their cart. | The items should be in stock. | 5
6 | Displays total amount | End user | Displays the total amount payable by the user within the cart. | Then after the correct details are entered, the user can proceed with the payment. | 5
7 | Order completion and email confirmation | End user | Shows the order summary and order confirmation is sent to the user's email. | Successful payment and then user can logout. | 5
8 | Administrator Login | Owner/Admin | Allows the owner to see the registered users and manage products. | Correct admin login credentials. | 5
9 | User Dashboard | End user | Shows the logged in user profile and previous orders by the user. | User must be logged in. | 5